## Backlog Tracker
Order | Epic | Backlog Item | Priority | Depends On | Impact | Prompt | Status | Notes
1 | Core Identity Provider | Keycloak cluster setup (HA, multi-node) | P0 | Technology Stack (backend runtime) | Foundation every other epic builds on — nothing else can start without a running Keycloak + DB | Implement: Keycloak cluster setup (HA, multi-node). Depends on: Technology Stack (backend runtime). Impact: Foundation every other epic builds on — nothing else can start without a running Keycloak + DB. | Backlog
2 | Core Identity Provider | Database backend decision + setup (Oracle 19c vs Postgres/Aurora) | P0 | Technology Stack (backend runtime) | Foundation every other epic builds on — nothing else can start without a running Keycloak + DB | Implement: Database backend decision + setup (Oracle 19c vs Postgres/Aurora). Depends on: Technology Stack (backend runtime). Impact: Foundation every other epic builds on — nothing else can start without a running Keycloak + DB. | Backlog
3 | Core Identity Provider | Realm strategy: realm-per-tenant (implied by auto-realm-creation requirement) | P0 | Technology Stack (backend runtime) | Foundation every other epic builds on — nothing else can start without a running Keycloak + DB | Implement: Realm strategy: realm-per-tenant (implied by auto-realm-creation requirement). Depends on: Technology Stack (backend runtime). Impact: Foundation every other epic builds on — nothing else can start without a running Keycloak + DB. | Backlog
4 | Core Identity Provider | Token signing strategy (RS256, JWKS publishing) | P0 | Technology Stack (backend runtime) | Foundation every other epic builds on — nothing else can start without a running Keycloak + DB | Implement: Token signing strategy (RS256, JWKS publishing). Depends on: Technology Stack (backend runtime). Impact: Foundation every other epic builds on — nothing else can start without a running Keycloak + DB. | Backlog
5 | Core Identity Provider | Session/token lifecycle policy (short-lived access, refresh rotation, forced revocation) | P0 | Technology Stack (backend runtime) | Foundation every other epic builds on — nothing else can start without a running Keycloak + DB | Implement: Session/token lifecycle policy (short-lived access, refresh rotation, forced revocation). Depends on: Technology Stack (backend runtime). Impact: Foundation every other epic builds on — nothing else can start without a running Keycloak + DB. | Backlog
6 | Security Parameters | Access token lifetime | P0 | None — can be decided in parallel with infra setup | Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live | Implement: Access token lifetime. Depends on: None — can be decided in parallel with infra setup. Impact: Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live. | Backlog
7 | Security Parameters | Refresh token lifetime + rotation policy | P0 | None — can be decided in parallel with infra setup | Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live | Implement: Refresh token lifetime + rotation policy. Depends on: None — can be decided in parallel with infra setup. Impact: Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live. | Backlog
8 | Security Parameters | SSO session idle / max lifespan | P0 | None — can be decided in parallel with infra setup | Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live | Implement: SSO session idle / max lifespan. Depends on: None — can be decided in parallel with infra setup. Impact: Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live. | Backlog
9 | Security Parameters | Password policy (length, complexity, history, hashing algorithm) | P0 | None — can be decided in parallel with infra setup | Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live | Implement: Password policy (length, complexity, history, hashing algorithm). Depends on: None — can be decided in parallel with infra setup. Impact: Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live. | Backlog
10 | Security Parameters | Brute-force detection thresholds (attempts, lockout duration) | P0 | None — can be decided in parallel with infra setup | Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live | Implement: Brute-force detection thresholds (attempts, lockout duration). Depends on: None — can be decided in parallel with infra setup. Impact: Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live. | Backlog
11 | Security Parameters | MFA enforcement matrix by role/tier | P0 | None — can be decided in parallel with infra setup | Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live | Implement: MFA enforcement matrix by role/tier. Depends on: None — can be decided in parallel with infra setup. Impact: Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live. | Backlog
12 | Security Parameters | TLS version + cipher suite requirements | P0 | None — can be decided in parallel with infra setup | Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live | Implement: TLS version + cipher suite requirements. Depends on: None — can be decided in parallel with infra setup. Impact: Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live. | Backlog
13 | Security Parameters | JWT signing algorithm + key rotation interval | P0 | None — can be decided in parallel with infra setup | Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live | Implement: JWT signing algorithm + key rotation interval. Depends on: None — can be decided in parallel with infra setup. Impact: Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live. | Backlog
14 | Security Parameters | Redirect URI / CORS allowlist (exact-match, no wildcards) | P0 | None — can be decided in parallel with infra setup | Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live | Implement: Redirect URI / CORS allowlist (exact-match, no wildcards). Depends on: None — can be decided in parallel with infra setup. Impact: Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live. | Backlog
15 | Security Parameters | PKCE enforcement for public clients | P0 | None — can be decided in parallel with infra setup | Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live | Implement: PKCE enforcement for public clients. Depends on: None — can be decided in parallel with infra setup. Impact: Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live. | Backlog
16 | Security Parameters | Admin console access restrictions (IP allowlist, mandatory MFA) | P0 | None — can be decided in parallel with infra setup | Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live | Implement: Admin console access restrictions (IP allowlist, mandatory MFA). Depends on: None — can be decided in parallel with infra setup. Impact: Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live. | Backlog
17 | Security Parameters | Audit log retention duration | P0 | None — can be decided in parallel with infra setup | Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live | Implement: Audit log retention duration. Depends on: None — can be decided in parallel with infra setup. Impact: Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live. | Backlog
18 | Security Parameters | Secrets/key rotation cadence | P0 | None — can be decided in parallel with infra setup | Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live | Implement: Secrets/key rotation cadence. Depends on: None — can be decided in parallel with infra setup. Impact: Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live. | Backlog
19 | Security Parameters | Rate limiting thresholds on token/login endpoints | P0 | None — can be decided in parallel with infra setup | Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live | Implement: Rate limiting thresholds on token/login endpoints. Depends on: None — can be decided in parallel with infra setup. Impact: Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live. | Backlog
20 | Security Parameters | Encryption at rest for tenant records (tenant name, metadata) | P0 | None — can be decided in parallel with infra setup | Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live | Implement: Encryption at rest for tenant records (tenant name, metadata). Depends on: None — can be decided in parallel with infra setup. Impact: Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live. | Backlog
21 | Security Parameters | Encryption at rest for user PII per tenant realm | P0 | None — can be decided in parallel with infra setup | Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live | Implement: Encryption at rest for user PII per tenant realm. Depends on: None — can be decided in parallel with infra setup. Impact: Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live. | Backlog
22 | Security Parameters | Verify client secret hashing enabled in Keycloak (not cleartext default) | P0 | None — can be decided in parallel with infra setup | Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live | Implement: Verify client secret hashing enabled in Keycloak (not cleartext default). Depends on: None — can be decided in parallel with infra setup. Impact: Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live. | Backlog
23 | Security Parameters | Per-tenant secrets storage for tenant-supplied integration API keys — encrypted, isolated per tenant, separate from platform's own Secrets Manager entries | P0 | None — can be decided in parallel with infra setup | Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live | Implement: Per-tenant secrets storage for tenant-supplied integration API keys — encrypted, isolated per tenant, separate from platform's own Secrets Manager entries. Depends on: None — can be decided in parallel with infra setup. Impact: Config values baked into every later auth flow; cheap to set now, expensive to retrofit after go-live. | Backlog
24 | Cloud Infrastructure (AWS) | Keycloak cluster hosting — EKS vs ECS, multi-AZ | P0 | Core Identity Provider (hosting target) | Determines where everything runs; blocks any real staging/prod deployment | Implement: Keycloak cluster hosting — EKS vs ECS, multi-AZ. Depends on: Core Identity Provider (hosting target). Impact: Determines where everything runs; blocks any real staging/prod deployment. | Backlog
25 | Cloud Infrastructure (AWS) | Database hosting — RDS (Oracle 19c) vs Aurora Postgres | P0 | Core Identity Provider (hosting target) | Determines where everything runs; blocks any real staging/prod deployment | Implement: Database hosting — RDS (Oracle 19c) vs Aurora Postgres. Depends on: Core Identity Provider (hosting target). Impact: Determines where everything runs; blocks any real staging/prod deployment. | Backlog
26 | Cloud Infrastructure (AWS) | Secrets/cert management via Secrets Manager or Parameter Store | P0 | Core Identity Provider (hosting target) | Determines where everything runs; blocks any real staging/prod deployment | Implement: Secrets/cert management via Secrets Manager or Parameter Store. Depends on: Core Identity Provider (hosting target). Impact: Determines where everything runs; blocks any real staging/prod deployment. | Backlog
27 | Cloud Infrastructure (AWS) | TLS termination — ALB + ACM | P0 | Core Identity Provider (hosting target) | Determines where everything runs; blocks any real staging/prod deployment | Implement: TLS termination — ALB + ACM. Depends on: Core Identity Provider (hosting target). Impact: Determines where everything runs; blocks any real staging/prod deployment. | Backlog
28 | Cloud Infrastructure (AWS) | DNS — Route53 | P0 | Core Identity Provider (hosting target) | Determines where everything runs; blocks any real staging/prod deployment | Implement: DNS — Route53. Depends on: Core Identity Provider (hosting target). Impact: Determines where everything runs; blocks any real staging/prod deployment. | Backlog
29 | Cloud Infrastructure (AWS) | Rate limiting / brute-force protection — WAF + Shield | P0 | Core Identity Provider (hosting target) | Determines where everything runs; blocks any real staging/prod deployment | Implement: Rate limiting / brute-force protection — WAF + Shield. Depends on: Core Identity Provider (hosting target). Impact: Determines where everything runs; blocks any real staging/prod deployment. | Backlog
30 | Cloud Infrastructure (AWS) | Observability — CloudWatch integration with Ops/Audit Console | P0 | Core Identity Provider (hosting target) | Determines where everything runs; blocks any real staging/prod deployment | Implement: Observability — CloudWatch integration with Ops/Audit Console. Depends on: Core Identity Provider (hosting target). Impact: Determines where everything runs; blocks any real staging/prod deployment. | Backlog
31 | Cloud Infrastructure (AWS) | Cross-region backup/restore for DR (RDS + realm config) | P0 | Core Identity Provider (hosting target) | Determines where everything runs; blocks any real staging/prod deployment | Implement: Cross-region backup/restore for DR (RDS + realm config). Depends on: Core Identity Provider (hosting target). Impact: Determines where everything runs; blocks any real staging/prod deployment. | Backlog
32 | Cloud Infrastructure (AWS) | Metering/billing event pipeline — Lambda/EventBridge | P0 | Core Identity Provider (hosting target) | Determines where everything runs; blocks any real staging/prod deployment | Implement: Metering/billing event pipeline — Lambda/EventBridge. Depends on: Core Identity Provider (hosting target). Impact: Determines where everything runs; blocks any real staging/prod deployment. | Backlog
33 | Cloud Infrastructure (AWS) | Confirm staying on Keycloak (not reopening as Cognito-vs-Keycloak) | P0 | Core Identity Provider (hosting target) | Determines where everything runs; blocks any real staging/prod deployment | Implement: Confirm staying on Keycloak (not reopening as Cognito-vs-Keycloak). Depends on: Core Identity Provider (hosting target). Impact: Determines where everything runs; blocks any real staging/prod deployment. | Backlog
34 | Cloud Infrastructure (AWS) | Auto-provision tenant subdomain (Route53 record) on signup, routed to Tenant Portal | P0 | Core Identity Provider (hosting target) | Determines where everything runs; blocks any real staging/prod deployment | Implement: Auto-provision tenant subdomain (Route53 record) on signup, routed to Tenant Portal. Depends on: Core Identity Provider (hosting target). Impact: Determines where everything runs; blocks any real staging/prod deployment. | Backlog
35 | Cloud Infrastructure (AWS) | Auto-issue/attach TLS certificate for new tenant subdomain (ACM) — wildcard vs per-subdomain issuance decision | P0 | Core Identity Provider (hosting target) | Determines where everything runs; blocks any real staging/prod deployment | Implement: Auto-issue/attach TLS certificate for new tenant subdomain (ACM) — wildcard vs per-subdomain issuance decision. Depends on: Core Identity Provider (hosting target). Impact: Determines where everything runs; blocks any real staging/prod deployment. | Backlog
36 | Containerization / Docker | Dockerize Keycloak (custom image with themes/extensions/Authenticator SPIs baked in) | P0 | Core Identity Provider, Technology Stack | Enables local dev/testing for every later epic; team velocity depends on this existing early | Implement: Dockerize Keycloak (custom image with themes/extensions/Authenticator SPIs baked in). Depends on: Core Identity Provider, Technology Stack. Impact: Enables local dev/testing for every later epic; team velocity depends on this existing early. | Backlog
37 | Containerization / Docker | Dockerize Identity Service API (Java 17 service) | P0 | Core Identity Provider, Technology Stack | Enables local dev/testing for every later epic; team velocity depends on this existing early | Implement: Dockerize Identity Service API (Java 17 service). Depends on: Core Identity Provider, Technology Stack. Impact: Enables local dev/testing for every later epic; team velocity depends on this existing early. | Backlog
38 | Containerization / Docker | Dockerize supporting subsystems (metering, billing webhook handler, admin portal backend) | P0 | Core Identity Provider, Technology Stack | Enables local dev/testing for every later epic; team velocity depends on this existing early | Implement: Dockerize supporting subsystems (metering, billing webhook handler, admin portal backend). Depends on: Core Identity Provider, Technology Stack. Impact: Enables local dev/testing for every later epic; team velocity depends on this existing early. | Backlog
39 | Containerization / Docker | Docker Compose stack for local dev/testing (Keycloak + Identity Service API + Postgres/Oracle + LDAP mock) | P0 | Core Identity Provider, Technology Stack | Enables local dev/testing for every later epic; team velocity depends on this existing early | Implement: Docker Compose stack for local dev/testing (Keycloak + Identity Service API + Postgres/Oracle + LDAP mock). Depends on: Core Identity Provider, Technology Stack. Impact: Enables local dev/testing for every later epic; team velocity depends on this existing early. | Backlog
40 | Containerization / Docker | Multi-stage builds — minimal runtime images, no build tooling in final image | P0 | Core Identity Provider, Technology Stack | Enables local dev/testing for every later epic; team velocity depends on this existing early | Implement: Multi-stage builds — minimal runtime images, no build tooling in final image. Depends on: Core Identity Provider, Technology Stack. Impact: Enables local dev/testing for every later epic; team velocity depends on this existing early. | Backlog
41 | Containerization / Docker | Base image security scanning (Trivy/similar) in CI pipeline | P0 | Core Identity Provider, Technology Stack | Enables local dev/testing for every later epic; team velocity depends on this existing early | Implement: Base image security scanning (Trivy/similar) in CI pipeline. Depends on: Core Identity Provider, Technology Stack. Impact: Enables local dev/testing for every later epic; team velocity depends on this existing early. | Backlog
42 | Containerization / Docker | Container registry — ECR, with image tagging/versioning strategy | P0 | Core Identity Provider, Technology Stack | Enables local dev/testing for every later epic; team velocity depends on this existing early | Implement: Container registry — ECR, with image tagging/versioning strategy. Depends on: Core Identity Provider, Technology Stack. Impact: Enables local dev/testing for every later epic; team velocity depends on this existing early. | Backlog
43 | Containerization / Docker | Externalized configuration/secrets — no secrets baked into images, injected via Secrets Manager at runtime | P0 | Core Identity Provider, Technology Stack | Enables local dev/testing for every later epic; team velocity depends on this existing early | Implement: Externalized configuration/secrets — no secrets baked into images, injected via Secrets Manager at runtime. Depends on: Core Identity Provider, Technology Stack. Impact: Enables local dev/testing for every later epic; team velocity depends on this existing early. | Backlog
44 | Containerization / Docker | Health check / liveness / readiness probes for each container | P0 | Core Identity Provider, Technology Stack | Enables local dev/testing for every later epic; team velocity depends on this existing early | Implement: Health check / liveness / readiness probes for each container. Depends on: Core Identity Provider, Technology Stack. Impact: Enables local dev/testing for every later epic; team velocity depends on this existing early. | Backlog
45 | Containerization / Docker | CI/CD pipeline: build, scan, push, deploy on merge | P0 | Core Identity Provider, Technology Stack | Enables local dev/testing for every later epic; team velocity depends on this existing early | Implement: CI/CD pipeline: build, scan, push, deploy on merge. Depends on: Core Identity Provider, Technology Stack. Impact: Enables local dev/testing for every later epic; team velocity depends on this existing early. | Backlog
46 | Containerization / Docker | Orchestration target — feeds into existing EKS vs ECS decision in the AWS epic | P0 | Core Identity Provider, Technology Stack | Enables local dev/testing for every later epic; team velocity depends on this existing early | Implement: Orchestration target — feeds into existing EKS vs ECS decision in the AWS epic. Depends on: Core Identity Provider, Technology Stack. Impact: Enables local dev/testing for every later epic; team velocity depends on this existing early. | Backlog
47 | Containerization / Docker | Full end-to-end docker-compose.yml — one command spins up Keycloak, Identity Service API, Super Admin Portal, Org Admin Portal, User Portal, DB, reverse proxy | P0 | Core Identity Provider, Technology Stack | Enables local dev/testing for every later epic; team velocity depends on this existing early | Implement: Full end-to-end docker-compose.yml — one command spins up Keycloak, Identity Service API, Super Admin Portal, Org Admin Portal, User Portal, DB, reverse proxy. Depends on: Core Identity Provider, Technology Stack. Impact: Enables local dev/testing for every later epic; team velocity depends on this existing early. | Backlog
48 | Containerization / Docker | Pre-configured Keycloak realm import on container startup (baseline realm/clients/roles/theme bootstrapped, not an empty instance) | P0 | Core Identity Provider, Technology Stack | Enables local dev/testing for every later epic; team velocity depends on this existing early | Implement: Pre-configured Keycloak realm import on container startup (baseline realm/clients/roles/theme bootstrapped, not an empty instance). Depends on: Core Identity Provider, Technology Stack. Impact: Enables local dev/testing for every later epic; team velocity depends on this existing early. | Backlog
49 | Containerization / Docker | Seed/demo data script — sample tenant + sample users so the stack is usable immediately after startup | P0 | Core Identity Provider, Technology Stack | Enables local dev/testing for every later epic; team velocity depends on this existing early | Implement: Seed/demo data script — sample tenant + sample users so the stack is usable immediately after startup. Depends on: Core Identity Provider, Technology Stack. Impact: Enables local dev/testing for every later epic; team velocity depends on this existing early. | Backlog
50 | Containerization / Docker | Startup ordering / health-check gating — DB ready, then Keycloak ready, then dependent services start (no race conditions) | P0 | Core Identity Provider, Technology Stack | Enables local dev/testing for every later epic; team velocity depends on this existing early | Implement: Startup ordering / health-check gating — DB ready, then Keycloak ready, then dependent services start (no race conditions). Depends on: Core Identity Provider, Technology Stack. Impact: Enables local dev/testing for every later epic; team velocity depends on this existing early. | Backlog
51 | Containerization / Docker | Reverse proxy/ingress container (nginx or Traefik) routing to each portal + Keycloak, mirroring domain-per-tenant routing locally | P0 | Core Identity Provider, Technology Stack | Enables local dev/testing for every later epic; team velocity depends on this existing early | Implement: Reverse proxy/ingress container (nginx or Traefik) routing to each portal + Keycloak, mirroring domain-per-tenant routing locally. Depends on: Core Identity Provider, Technology Stack. Impact: Enables local dev/testing for every later epic; team velocity depends on this existing early. | Backlog
52 | Containerization / Docker | Single documented onboarding command (docker-compose up / make up) for new developers — no manual setup steps | P0 | Core Identity Provider, Technology Stack | Enables local dev/testing for every later epic; team velocity depends on this existing early | Implement: Single documented onboarding command (docker-compose up / make up) for new developers — no manual setup steps. Depends on: Core Identity Provider, Technology Stack. Impact: Enables local dev/testing for every later epic; team velocity depends on this existing early. | Backlog
53 | Containerization / Docker | Environment parity — same images/compose definitions form the basis for staging/production, not a throwaway dev-only setup | P0 | Core Identity Provider, Technology Stack | Enables local dev/testing for every later epic; team velocity depends on this existing early | Implement: Environment parity — same images/compose definitions form the basis for staging/production, not a throwaway dev-only setup. Depends on: Core Identity Provider, Technology Stack. Impact: Enables local dev/testing for every later epic; team velocity depends on this existing early. | Backlog
54 | Technology Stack | Backend runtime: Node.js — applies to Identity Service API, metering, billing webhook handler, portal backends | P0 | None — foundational decision | Determines every later implementation choice (frameworks, hiring, tooling); must be settled before any code is written | Implement: Backend runtime: Node.js — applies to Identity Service API, metering, billing webhook handler, portal backends. Depends on: None — foundational decision. Impact: Determines every later implementation choice (frameworks, hiring, tooling); must be settled before any code is written. | Backlog
55 | Technology Stack | Backend framework decision: Express vs NestJS vs Fastify | P0 | None — foundational decision | Determines every later implementation choice (frameworks, hiring, tooling); must be settled before any code is written | Implement: Backend framework decision: Express vs NestJS vs Fastify. Depends on: None — foundational decision. Impact: Determines every later implementation choice (frameworks, hiring, tooling); must be settled before any code is written. | Backlog
56 | Technology Stack | Frontend framework decision: React/Next.js vs Vue/Nuxt vs other (Node.js ecosystem) | P0 | None — foundational decision | Determines every later implementation choice (frameworks, hiring, tooling); must be settled before any code is written | Implement: Frontend framework decision: React/Next.js vs Vue/Nuxt vs other (Node.js ecosystem). Depends on: None — foundational decision. Impact: Determines every later implementation choice (frameworks, hiring, tooling); must be settled before any code is written. | Backlog
57 | Technology Stack | Reconcile with existing JWT-validation-SDK item — Java/Python SDKs are for consuming apps (BOE/D3OS/Matcha), not this system's own backend; add Node.js SDK variant if any consuming services are Node-based | P0 | None — foundational decision | Determines every later implementation choice (frameworks, hiring, tooling); must be settled before any code is written | Implement: Reconcile with existing JWT-validation-SDK item — Java/Python SDKs are for consuming apps (BOE/D3OS/Matcha), not this system's own backend; add Node.js SDK variant if any consuming services are Node-based. Depends on: None — foundational decision. Impact: Determines every later implementation choice (frameworks, hiring, tooling); must be settled before any code is written. | Backlog
58 | Technology Stack | Confirm this is a deliberate separate Node-based build vs the stated Java/Oracle/BOE primary stack (scope check, not assumed) | P0 | None — foundational decision | Determines every later implementation choice (frameworks, hiring, tooling); must be settled before any code is written | Implement: Confirm this is a deliberate separate Node-based build vs the stated Java/Oracle/BOE primary stack (scope check, not assumed). Depends on: None — foundational decision. Impact: Determines every later implementation choice (frameworks, hiring, tooling); must be settled before any code is written. | Backlog
59 | Directory Federation (LDAP/AD) | Confirm whether existing LDAP directory is AD or AD-compatible | P0 | Core Identity Provider | Real users can't authenticate via the existing directory until this is done; blocks realistic SAML/OIDC testing | Implement: Confirm whether existing LDAP directory is AD or AD-compatible. Depends on: Core Identity Provider. Impact: Real users can't authenticate via the existing directory until this is done; blocks realistic SAML/OIDC testing. | Backlog
60 | Directory Federation (LDAP/AD) | LDAP/AD federation into Keycloak (reuse existing UPN objectClass work) | P0 | Core Identity Provider | Real users can't authenticate via the existing directory until this is done; blocks realistic SAML/OIDC testing | Implement: LDAP/AD federation into Keycloak (reuse existing UPN objectClass work). Depends on: Core Identity Provider. Impact: Real users can't authenticate via the existing directory until this is done; blocks realistic SAML/OIDC testing. | Backlog
61 | Directory Federation (LDAP/AD) | Group/role sync from directory | P0 | Core Identity Provider | Real users can't authenticate via the existing directory until this is done; blocks realistic SAML/OIDC testing | Implement: Group/role sync from directory. Depends on: Core Identity Provider. Impact: Real users can't authenticate via the existing directory until this is done; blocks realistic SAML/OIDC testing. | Backlog
62 | Directory Federation (LDAP/AD) | Kerberos/NTLM SSO for domain-joined desktop clients (if needed) | P0 | Core Identity Provider | Real users can't authenticate via the existing directory until this is done; blocks realistic SAML/OIDC testing | Implement: Kerberos/NTLM SSO for domain-joined desktop clients (if needed). Depends on: Core Identity Provider. Impact: Real users can't authenticate via the existing directory until this is done; blocks realistic SAML/OIDC testing. | Backlog
63 | Directory Federation (LDAP/AD) | Azure AD/Entra ID federation (if separate cloud AD tenant exists) | P0 | Core Identity Provider | Real users can't authenticate via the existing directory until this is done; blocks realistic SAML/OIDC testing | Implement: Azure AD/Entra ID federation (if separate cloud AD tenant exists). Depends on: Core Identity Provider. Impact: Real users can't authenticate via the existing directory until this is done; blocks realistic SAML/OIDC testing. | Backlog
64 | Directory Federation (LDAP/AD) | LDAP Ops: live sync vs periodic sync vs on-demand lookup | P0 | Core Identity Provider | Real users can't authenticate via the existing directory until this is done; blocks realistic SAML/OIDC testing | Implement: LDAP Ops: live sync vs periodic sync vs on-demand lookup. Depends on: Core Identity Provider. Impact: Real users can't authenticate via the existing directory until this is done; blocks realistic SAML/OIDC testing. | Backlog
65 | Directory Federation (LDAP/AD) | LDAP write-back support decision (password resets pushed to AD?) | P0 | Core Identity Provider | Real users can't authenticate via the existing directory until this is done; blocks realistic SAML/OIDC testing | Implement: LDAP write-back support decision (password resets pushed to AD?). Depends on: Core Identity Provider. Impact: Real users can't authenticate via the existing directory until this is done; blocks realistic SAML/OIDC testing. | Backlog
66 | Directory Federation (LDAP/AD) | LDAP connection pooling/failover | P0 | Core Identity Provider | Real users can't authenticate via the existing directory until this is done; blocks realistic SAML/OIDC testing | Implement: LDAP connection pooling/failover. Depends on: Core Identity Provider. Impact: Real users can't authenticate via the existing directory until this is done; blocks realistic SAML/OIDC testing. | Backlog
67 | Directory Federation (LDAP/AD) | LDAP sync scheduling and conflict resolution | P0 | Core Identity Provider | Real users can't authenticate via the existing directory until this is done; blocks realistic SAML/OIDC testing | Implement: LDAP sync scheduling and conflict resolution. Depends on: Core Identity Provider. Impact: Real users can't authenticate via the existing directory until this is done; blocks realistic SAML/OIDC testing. | Backlog
68 | Directory Federation (LDAP/AD) | LDAP-specific error handling surfaced to tenant admins | P0 | Core Identity Provider | Real users can't authenticate via the existing directory until this is done; blocks realistic SAML/OIDC testing | Implement: LDAP-specific error handling surfaced to tenant admins. Depends on: Core Identity Provider. Impact: Real users can't authenticate via the existing directory until this is done; blocks realistic SAML/OIDC testing. | Backlog
69 | Governance & Control Plane | Ownership model (who approves registrations, owns realm policy) | P0 | Core Identity Provider | Defines who can change what; needed before more than one person operates the system | Implement: Ownership model (who approves registrations, owns realm policy). Depends on: Core Identity Provider. Impact: Defines who can change what; needed before more than one person operates the system. | Backlog
70 | Governance & Control Plane | Change control process for Keycloak upgrades/realm config changes | P0 | Core Identity Provider | Defines who can change what; needed before more than one person operates the system | Implement: Change control process for Keycloak upgrades/realm config changes. Depends on: Core Identity Provider. Impact: Defines who can change what; needed before more than one person operates the system. | Backlog
71 | Governance & Control Plane | Decision: D3OS-integrated control plane vs standalone | P0 | Core Identity Provider | Defines who can change what; needed before more than one person operates the system | Implement: Decision: D3OS-integrated control plane vs standalone. Depends on: Core Identity Provider. Impact: Defines who can change what; needed before more than one person operates the system. | Backlog
72 | SAML Integration | Keycloak as SAML 2.0 IdP | P1 | Core Identity Provider, Directory Federation (LDAP/AD) | Unblocks BOE SSO — a named, concrete business requirement | Implement: Keycloak as SAML 2.0 IdP. Depends on: Core Identity Provider, Directory Federation (LDAP/AD). Impact: Unblocks BOE SSO — a named, concrete business requirement. | Backlog
73 | SAML Integration | BOE as SAML SP — attribute/NameID mapping | P1 | Core Identity Provider, Directory Federation (LDAP/AD) | Unblocks BOE SSO — a named, concrete business requirement | Implement: BOE as SAML SP — attribute/NameID mapping. Depends on: Core Identity Provider, Directory Federation (LDAP/AD). Impact: Unblocks BOE SSO — a named, concrete business requirement. | Backlog
74 | SAML Integration | Trusted auth end-to-end test with BOE | P1 | Core Identity Provider, Directory Federation (LDAP/AD) | Unblocks BOE SSO — a named, concrete business requirement | Implement: Trusted auth end-to-end test with BOE. Depends on: Core Identity Provider, Directory Federation (LDAP/AD). Impact: Unblocks BOE SSO — a named, concrete business requirement. | Backlog
75 | SAML Integration | SAML assertion tampering/replay + XXE review | P1 | Core Identity Provider, Directory Federation (LDAP/AD) | Unblocks BOE SSO — a named, concrete business requirement | Implement: SAML assertion tampering/replay + XXE review. Depends on: Core Identity Provider, Directory Federation (LDAP/AD). Impact: Unblocks BOE SSO — a named, concrete business requirement. | Backlog
76 | OIDC / App Authentication | Client registration process for OIDC apps (Auth Code + PKCE) | P1 | Core Identity Provider, Directory Federation (LDAP/AD) | Unblocks every new/internal app integration | Implement: Client registration process for OIDC apps (Auth Code + PKCE). Depends on: Core Identity Provider, Directory Federation (LDAP/AD). Impact: Unblocks every new/internal app integration. | Backlog
77 | OIDC / App Authentication | Pilot app integration (lowest-risk internal tool first) | P1 | Core Identity Provider, Directory Federation (LDAP/AD) | Unblocks every new/internal app integration | Implement: Pilot app integration (lowest-risk internal tool first). Depends on: Core Identity Provider, Directory Federation (LDAP/AD). Impact: Unblocks every new/internal app integration. | Backlog
78 | OIDC / App Authentication | SSO validation across SAML (BOE) + OIDC apps | P1 | Core Identity Provider, Directory Federation (LDAP/AD) | Unblocks every new/internal app integration | Implement: SSO validation across SAML (BOE) + OIDC apps. Depends on: Core Identity Provider, Directory Federation (LDAP/AD). Impact: Unblocks every new/internal app integration. | Backlog
79 | API Authentication | Client Credentials grant for service-to-service | P1 | Core Identity Provider | Unblocks service-to-service auth; required before any backend API can enforce access control | Implement: Client Credentials grant for service-to-service. Depends on: Core Identity Provider. Impact: Unblocks service-to-service auth; required before any backend API can enforce access control. | Backlog
80 | API Authentication | Shared JWT-validation library — Java (Corretto 17) and Python | P1 | Core Identity Provider | Unblocks service-to-service auth; required before any backend API can enforce access control | Implement: Shared JWT-validation library — Java (Corretto 17) and Python. Depends on: Core Identity Provider. Impact: Unblocks service-to-service auth; required before any backend API can enforce access control. | Backlog
81 | API Authentication | JWKS caching strategy in resource servers | P1 | Core Identity Provider | Unblocks service-to-service auth; required before any backend API can enforce access control | Implement: JWKS caching strategy in resource servers. Depends on: Core Identity Provider. Impact: Unblocks service-to-service auth; required before any backend API can enforce access control. | Backlog
82 | MFA | TOTP enforcement for privileged/admin roles | P1 | OIDC / App Authentication, SAML Integration | Adds the required security layer on top of already-working login flows | Implement: TOTP enforcement for privileged/admin roles. Depends on: OIDC / App Authentication, SAML Integration. Impact: Adds the required security layer on top of already-working login flows. | Backlog
83 | MFA | WebAuthn/FIDO2 support | P1 | OIDC / App Authentication, SAML Integration | Adds the required security layer on top of already-working login flows | Implement: WebAuthn/FIDO2 support. Depends on: OIDC / App Authentication, SAML Integration. Impact: Adds the required security layer on top of already-working login flows. | Backlog
84 | MFA | Conditional/step-up MFA based on risk | P1 | OIDC / App Authentication, SAML Integration | Adds the required security layer on top of already-working login flows | Implement: Conditional/step-up MFA based on risk. Depends on: OIDC / App Authentication, SAML Integration. Impact: Adds the required security layer on top of already-working login flows. | Backlog
85 | MFA | MFA bypass prevention for federated (social/SAML) logins | P1 | OIDC / App Authentication, SAML Integration | Adds the required security layer on top of already-working login flows | Implement: MFA bypass prevention for federated (social/SAML) logins. Depends on: OIDC / App Authentication, SAML Integration. Impact: Adds the required security layer on top of already-working login flows. | Backlog
86 | MFA | Lost-MFA-device recovery flow | P1 | OIDC / App Authentication, SAML Integration | Adds the required security layer on top of already-working login flows | Implement: Lost-MFA-device recovery flow. Depends on: OIDC / App Authentication, SAML Integration. Impact: Adds the required security layer on top of already-working login flows. | Backlog
87 | Authorization | RBAC via Keycloak roles/groups | P1 | OIDC / App Authentication, API Authentication | Without this, 'authenticated' incorrectly implies 'allowed' — a real security gap if skipped | Implement: RBAC via Keycloak roles/groups. Depends on: OIDC / App Authentication, API Authentication. Impact: Without this, 'authenticated' incorrectly implies 'allowed' — a real security gap if skipped. | Backlog
88 | Authorization | Fine-grained authorization (UMA 2.0) — evaluate, defer unless needed | P1 | OIDC / App Authentication, API Authentication | Without this, 'authenticated' incorrectly implies 'allowed' — a real security gap if skipped | Implement: Fine-grained authorization (UMA 2.0) — evaluate, defer unless needed. Depends on: OIDC / App Authentication, API Authentication. Impact: Without this, 'authenticated' incorrectly implies 'allowed' — a real security gap if skipped. | Backlog
89 | Authorization | Clear separation of authentication vs authorization enforcement in apps | P1 | OIDC / App Authentication, API Authentication | Without this, 'authenticated' incorrectly implies 'allowed' — a real security gap if skipped | Implement: Clear separation of authentication vs authorization enforcement in apps. Depends on: OIDC / App Authentication, API Authentication. Impact: Without this, 'authenticated' incorrectly implies 'allowed' — a real security gap if skipped. | Backlog
90 | Social Login | Google | P1 | OIDC / App Authentication | Expands login options and conversion; not required for core function | Implement: Google. Depends on: OIDC / App Authentication. Impact: Expands login options and conversion; not required for core function. | Backlog
91 | Social Login | Microsoft/Entra | P1 | OIDC / App Authentication | Expands login options and conversion; not required for core function | Implement: Microsoft/Entra. Depends on: OIDC / App Authentication. Impact: Expands login options and conversion; not required for core function. | Backlog
92 | Social Login | Facebook | P1 | OIDC / App Authentication | Expands login options and conversion; not required for core function | Implement: Facebook. Depends on: OIDC / App Authentication. Impact: Expands login options and conversion; not required for core function. | Backlog
93 | Social Login | GitHub | P1 | OIDC / App Authentication | Expands login options and conversion; not required for core function | Implement: GitHub. Depends on: OIDC / App Authentication. Impact: Expands login options and conversion; not required for core function. | Backlog
94 | Social Login | Account-linking policy across providers + LDAP/email signups | P1 | OIDC / App Authentication | Expands login options and conversion; not required for core function | Implement: Account-linking policy across providers + LDAP/email signups. Depends on: OIDC / App Authentication. Impact: Expands login options and conversion; not required for core function. | Backlog
95 | Social Login | Step-up MFA applied to federated logins (not bypassed) | P1 | OIDC / App Authentication | Expands login options and conversion; not required for core function | Implement: Step-up MFA applied to federated logins (not bypassed). Depends on: OIDC / App Authentication. Impact: Expands login options and conversion; not required for core function. | Backlog
96 | Social Login | Tenant/plan entitlement gating for social login | P1 | OIDC / App Authentication | Expands login options and conversion; not required for core function | Implement: Tenant/plan entitlement gating for social login. Depends on: OIDC / App Authentication. Impact: Expands login options and conversion; not required for core function. | Backlog
97 | WhatsApp Integration | Decide scope: full login method vs OTP/MFA channel | P1 | MFA (as an OTP channel) | Adds a phone-based auth option; valuable for phone-only users, not core-path | Implement: Decide scope: full login method vs OTP/MFA channel. Depends on: MFA (as an OTP channel). Impact: Adds a phone-based auth option; valuable for phone-only users, not core-path. | Backlog
98 | WhatsApp Integration | WhatsApp Business API access (Meta Cloud API or BSP) | P1 | MFA (as an OTP channel) | Adds a phone-based auth option; valuable for phone-only users, not core-path | Implement: WhatsApp Business API access (Meta Cloud API or BSP). Depends on: MFA (as an OTP channel). Impact: Adds a phone-based auth option; valuable for phone-only users, not core-path. | Backlog
99 | WhatsApp Integration | Custom Keycloak Authenticator SPI (Java) for send/verify OTP | P1 | MFA (as an OTP channel) | Adds a phone-based auth option; valuable for phone-only users, not core-path | Implement: Custom Keycloak Authenticator SPI (Java) for send/verify OTP. Depends on: MFA (as an OTP channel). Impact: Adds a phone-based auth option; valuable for phone-only users, not core-path. | Backlog
100 | WhatsApp Integration | Cost model — feeds subscription/plan gating | P1 | MFA (as an OTP channel) | Adds a phone-based auth option; valuable for phone-only users, not core-path | Implement: Cost model — feeds subscription/plan gating. Depends on: MFA (as an OTP channel). Impact: Adds a phone-based auth option; valuable for phone-only users, not core-path. | Backlog
101 | WhatsApp Integration | SMS fallback if WhatsApp delivery fails | P1 | MFA (as an OTP channel) | Adds a phone-based auth option; valuable for phone-only users, not core-path | Implement: SMS fallback if WhatsApp delivery fails. Depends on: MFA (as an OTP channel). Impact: Adds a phone-based auth option; valuable for phone-only users, not core-path. | Backlog
102 | Multiple IDPs (Identity Brokering) | IDP selection screen behavior | P1 | Social Login, SAML Integration, Directory Federation (LDAP/AD) | Formalizes/governs IDPs already built individually; mostly policy and UX work at this point | Implement: IDP selection screen behavior. Depends on: Social Login, SAML Integration, Directory Federation (LDAP/AD). Impact: Formalizes/governs IDPs already built individually; mostly policy and UX work at this point. | Backlog
103 | Multiple IDPs (Identity Brokering) | Default/primary IDP per tenant | P1 | Social Login, SAML Integration, Directory Federation (LDAP/AD) | Formalizes/governs IDPs already built individually; mostly policy and UX work at this point | Implement: Default/primary IDP per tenant. Depends on: Social Login, SAML Integration, Directory Federation (LDAP/AD). Impact: Formalizes/governs IDPs already built individually; mostly policy and UX work at this point. | Backlog
104 | Multiple IDPs (Identity Brokering) | Consistent account-linking policy across all IDP types | P1 | Social Login, SAML Integration, Directory Federation (LDAP/AD) | Formalizes/governs IDPs already built individually; mostly policy and UX work at this point | Implement: Consistent account-linking policy across all IDP types. Depends on: Social Login, SAML Integration, Directory Federation (LDAP/AD). Impact: Formalizes/governs IDPs already built individually; mostly policy and UX work at this point. | Backlog
105 | Multiple IDPs (Identity Brokering) | Per-tenant IDP enablement (feature flag + plan gated) | P1 | Social Login, SAML Integration, Directory Federation (LDAP/AD) | Formalizes/governs IDPs already built individually; mostly policy and UX work at this point | Implement: Per-tenant IDP enablement (feature flag + plan gated). Depends on: Social Login, SAML Integration, Directory Federation (LDAP/AD). Impact: Formalizes/governs IDPs already built individually; mostly policy and UX work at this point. | Backlog
106 | Authenticator Integrator | Pluggable authenticator plugin interface (Keycloak Authenticator SPI) | P1 | MFA, WhatsApp Integration | Makes adding future auth methods cheap — engineering leverage, not user-facing on its own | Implement: Pluggable authenticator plugin interface (Keycloak Authenticator SPI). Depends on: MFA, WhatsApp Integration. Impact: Makes adding future auth methods cheap — engineering leverage, not user-facing on its own. | Backlog
107 | Authenticator Integrator | Registry/catalog of available authenticators | P1 | MFA, WhatsApp Integration | Makes adding future auth methods cheap — engineering leverage, not user-facing on its own | Implement: Registry/catalog of available authenticators. Depends on: MFA, WhatsApp Integration. Impact: Makes adding future auth methods cheap — engineering leverage, not user-facing on its own. | Backlog
108 | Authenticator Integrator | Per-tenant enablement from Super-Admin-allowed set | P1 | MFA, WhatsApp Integration | Makes adding future auth methods cheap — engineering leverage, not user-facing on its own | Implement: Per-tenant enablement from Super-Admin-allowed set. Depends on: MFA, WhatsApp Integration. Impact: Makes adding future auth methods cheap — engineering leverage, not user-facing on its own. | Backlog
109 | Service Layer (Identity-as-a-Service) | Identity Service API wrapping Keycloak admin API | P2 | Core Identity Provider, OIDC / App Authentication, API Authentication | Unblocks self-service onboarding; without it, every tenant needs manual admin setup | Implement: Identity Service API wrapping Keycloak admin API. Depends on: Core Identity Provider, OIDC / App Authentication, API Authentication. Impact: Unblocks self-service onboarding; without it, every tenant needs manual admin setup. | Backlog
110 | Service Layer (Identity-as-a-Service) | Self-service client/app registration endpoint | P2 | Core Identity Provider, OIDC / App Authentication, API Authentication | Unblocks self-service onboarding; without it, every tenant needs manual admin setup | Implement: Self-service client/app registration endpoint. Depends on: Core Identity Provider, OIDC / App Authentication, API Authentication. Impact: Unblocks self-service onboarding; without it, every tenant needs manual admin setup. | Backlog
111 | Service Layer (Identity-as-a-Service) | Environment separation (dev/staging/prod) | P2 | Core Identity Provider, OIDC / App Authentication, API Authentication | Unblocks self-service onboarding; without it, every tenant needs manual admin setup | Implement: Environment separation (dev/staging/prod). Depends on: Core Identity Provider, OIDC / App Authentication, API Authentication. Impact: Unblocks self-service onboarding; without it, every tenant needs manual admin setup. | Backlog
112 | Service Layer (Identity-as-a-Service) | API/SDK versioning + deprecation policy | P2 | Core Identity Provider, OIDC / App Authentication, API Authentication | Unblocks self-service onboarding; without it, every tenant needs manual admin setup | Implement: API/SDK versioning + deprecation policy. Depends on: Core Identity Provider, OIDC / App Authentication, API Authentication. Impact: Unblocks self-service onboarding; without it, every tenant needs manual admin setup. | Backlog
113 | Service Layer (Identity-as-a-Service) | Automated realm creation on tenant signup | P2 | Core Identity Provider, OIDC / App Authentication, API Authentication | Unblocks self-service onboarding; without it, every tenant needs manual admin setup | Implement: Automated realm creation on tenant signup. Depends on: Core Identity Provider, OIDC / App Authentication, API Authentication. Impact: Unblocks self-service onboarding; without it, every tenant needs manual admin setup. | Backlog
114 | Service Layer (Identity-as-a-Service) | Realm blueprint/template with default security parameters | P2 | Core Identity Provider, OIDC / App Authentication, API Authentication | Unblocks self-service onboarding; without it, every tenant needs manual admin setup | Implement: Realm blueprint/template with default security parameters. Depends on: Core Identity Provider, OIDC / App Authentication, API Authentication. Impact: Unblocks self-service onboarding; without it, every tenant needs manual admin setup. | Backlog
115 | Service Layer (Identity-as-a-Service) | Rollback/retry strategy for partial realm-creation failures | P2 | Core Identity Provider, OIDC / App Authentication, API Authentication | Unblocks self-service onboarding; without it, every tenant needs manual admin setup | Implement: Rollback/retry strategy for partial realm-creation failures. Depends on: Core Identity Provider, OIDC / App Authentication, API Authentication. Impact: Unblocks self-service onboarding; without it, every tenant needs manual admin setup. | Backlog
116 | Service Layer (Identity-as-a-Service) | On tenant signup — orchestrate realm creation AND subdomain/domain provisioning as one transaction (rollback both if either step fails) | P2 | Core Identity Provider, OIDC / App Authentication, API Authentication | Unblocks self-service onboarding; without it, every tenant needs manual admin setup | Implement: On tenant signup — orchestrate realm creation AND subdomain/domain provisioning as one transaction (rollback both if either step fails). Depends on: Core Identity Provider, OIDC / App Authentication, API Authentication. Impact: Unblocks self-service onboarding; without it, every tenant needs manual admin setup. | Backlog
117 | Multi-Tenancy | Tenant isolation model — realm-per-tenant (confirmed direction) | P2 | Service Layer (Identity-as-a-Service) | Unblocks running more than one customer on the platform at all | Implement: Tenant isolation model — realm-per-tenant (confirmed direction). Depends on: Service Layer (Identity-as-a-Service). Impact: Unblocks running more than one customer on the platform at all. | Backlog
118 | Multi-Tenancy | Tenant-scoped roles/groups | P2 | Service Layer (Identity-as-a-Service) | Unblocks running more than one customer on the platform at all | Implement: Tenant-scoped roles/groups. Depends on: Service Layer (Identity-as-a-Service). Impact: Unblocks running more than one customer on the platform at all. | Backlog
119 | Multi-Tenancy | Automated end-user self-signup flow per tenant realm | P2 | Service Layer (Identity-as-a-Service) | Unblocks running more than one customer on the platform at all | Implement: Automated end-user self-signup flow per tenant realm. Depends on: Service Layer (Identity-as-a-Service). Impact: Unblocks running more than one customer on the platform at all. | Backlog
120 | Multi-Tenancy | Email verification on signup | P2 | Service Layer (Identity-as-a-Service) | Unblocks running more than one customer on the platform at all | Implement: Email verification on signup. Depends on: Service Layer (Identity-as-a-Service). Impact: Unblocks running more than one customer on the platform at all. | Backlog
121 | Multi-Tenancy | Plan-tier user-count enforcement at signup time | P2 | Service Layer (Identity-as-a-Service) | Unblocks running more than one customer on the platform at all | Implement: Plan-tier user-count enforcement at signup time. Depends on: Service Layer (Identity-as-a-Service). Impact: Unblocks running more than one customer on the platform at all. | Backlog
122 | Multi-Tenancy | Admin-approval-gated vs open self-registration (tenant-configurable) | P2 | Service Layer (Identity-as-a-Service) | Unblocks running more than one customer on the platform at all | Implement: Admin-approval-gated vs open self-registration (tenant-configurable). Depends on: Service Layer (Identity-as-a-Service). Impact: Unblocks running more than one customer on the platform at all. | Backlog
123 | Multi-Tenancy | Domain-to-realm routing — new tenant subdomain must map to the correct Keycloak realm at the ingress/routing layer | P2 | Service Layer (Identity-as-a-Service) | Unblocks running more than one customer on the platform at all | Implement: Domain-to-realm routing — new tenant subdomain must map to the correct Keycloak realm at the ingress/routing layer. Depends on: Service Layer (Identity-as-a-Service). Impact: Unblocks running more than one customer on the platform at all. | Backlog
124 | User Import/Export | Defined, versioned import schema (strict template) | P2 | Multi-Tenancy, Directory Federation (LDAP/AD) | Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed | Implement: Defined, versioned import schema (strict template). Depends on: Multi-Tenancy, Directory Federation (LDAP/AD). Impact: Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed. | Backlog
125 | User Import/Export | Full field/type/format validation before any DB write | P2 | Multi-Tenancy, Directory Federation (LDAP/AD) | Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed | Implement: Full field/type/format validation before any DB write. Depends on: Multi-Tenancy, Directory Federation (LDAP/AD). Impact: Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed. | Backlog
126 | User Import/Export | Duplicate detection (within file + against existing tenant users) | P2 | Multi-Tenancy, Directory Federation (LDAP/AD) | Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed | Implement: Duplicate detection (within file + against existing tenant users). Depends on: Multi-Tenancy, Directory Federation (LDAP/AD). Impact: Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed. | Backlog
127 | User Import/Export | Plan-tier user-limit enforcement during import | P2 | Multi-Tenancy, Directory Federation (LDAP/AD) | Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed | Implement: Plan-tier user-limit enforcement during import. Depends on: Multi-Tenancy, Directory Federation (LDAP/AD). Impact: Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed. | Backlog
128 | User Import/Export | Injection-safe parsing | P2 | Multi-Tenancy, Directory Federation (LDAP/AD) | Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed | Implement: Injection-safe parsing. Depends on: Multi-Tenancy, Directory Federation (LDAP/AD). Impact: Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed. | Backlog
129 | User Import/Export | Dry-run/preview mode with per-row error reporting | P2 | Multi-Tenancy, Directory Federation (LDAP/AD) | Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed | Implement: Dry-run/preview mode with per-row error reporting. Depends on: Multi-Tenancy, Directory Federation (LDAP/AD). Impact: Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed. | Backlog
130 | User Import/Export | Admin-only, tenant-scoped authorization to trigger import | P2 | Multi-Tenancy, Directory Federation (LDAP/AD) | Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed | Implement: Admin-only, tenant-scoped authorization to trigger import. Depends on: Multi-Tenancy, Directory Federation (LDAP/AD). Impact: Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed. | Backlog
131 | User Import/Export | File size/row count limits (anti-DoS) | P2 | Multi-Tenancy, Directory Federation (LDAP/AD) | Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed | Implement: File size/row count limits (anti-DoS). Depends on: Multi-Tenancy, Directory Federation (LDAP/AD). Impact: Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed. | Backlog
132 | User Import/Export | Async job processing with full audit trail | P2 | Multi-Tenancy, Directory Federation (LDAP/AD) | Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed | Implement: Async job processing with full audit trail. Depends on: Multi-Tenancy, Directory Federation (LDAP/AD). Impact: Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed. | Backlog
133 | User Import/Export | Password-import strategy — forced reset vs compatible hash vs federation | P2 | Multi-Tenancy, Directory Federation (LDAP/AD) | Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed | Implement: Password-import strategy — forced reset vs compatible hash vs federation. Depends on: Multi-Tenancy, Directory Federation (LDAP/AD). Impact: Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed. | Backlog
134 | User Import/Export | AD/LDAP import source — live federation vs one-time sync (architectural fork) | P2 | Multi-Tenancy, Directory Federation (LDAP/AD) | Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed | Implement: AD/LDAP import source — live federation vs one-time sync (architectural fork). Depends on: Multi-Tenancy, Directory Federation (LDAP/AD). Impact: Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed. | Backlog
135 | User Import/Export | CSV import adapter | P2 | Multi-Tenancy, Directory Federation (LDAP/AD) | Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed | Implement: CSV import adapter. Depends on: Multi-Tenancy, Directory Federation (LDAP/AD). Impact: Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed. | Backlog
136 | User Import/Export | Excel (.xlsx) import adapter — separate parser from CSV | P2 | Multi-Tenancy, Directory Federation (LDAP/AD) | Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed | Implement: Excel (.xlsx) import adapter — separate parser from CSV. Depends on: Multi-Tenancy, Directory Federation (LDAP/AD). Impact: Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed. | Backlog
137 | User Import/Export | API-based import — authenticated endpoint, single and bulk | P2 | Multi-Tenancy, Directory Federation (LDAP/AD) | Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed | Implement: API-based import — authenticated endpoint, single and bulk. Depends on: Multi-Tenancy, Directory Federation (LDAP/AD). Impact: Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed. | Backlog
138 | User Import/Export | Single-user add routed through same validation pipeline as bulk | P2 | Multi-Tenancy, Directory Federation (LDAP/AD) | Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed | Implement: Single-user add routed through same validation pipeline as bulk. Depends on: Multi-Tenancy, Directory Federation (LDAP/AD). Impact: Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed. | Backlog
139 | User Import/Export | Shared validation/import core used by all adapters | P2 | Multi-Tenancy, Directory Federation (LDAP/AD) | Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed | Implement: Shared validation/import core used by all adapters. Depends on: Multi-Tenancy, Directory Federation (LDAP/AD). Impact: Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed. | Backlog
140 | User Import/Export | Bulk user export (tenant-initiated, offboarding/compliance) | P2 | Multi-Tenancy, Directory Federation (LDAP/AD) | Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed | Implement: Bulk user export (tenant-initiated, offboarding/compliance). Depends on: Multi-Tenancy, Directory Federation (LDAP/AD). Impact: Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed. | Backlog
141 | User Import/Export | Link export mechanism to existing DR/backup epic | P2 | Multi-Tenancy, Directory Federation (LDAP/AD) | Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed | Implement: Link export mechanism to existing DR/backup epic. Depends on: Multi-Tenancy, Directory Federation (LDAP/AD). Impact: Unblocks realistic tenant onboarding at scale — 20K-user tenants can't be hand-typed. | Backlog
142 | Portals | User Portal — profile, sessions, MFA enrollment, password reset, login history | P2 | Service Layer (Identity-as-a-Service), Multi-Tenancy, Feature Flag / Global Control | The actual product surface — nothing is usable by a human without it | Implement: User Portal — profile, sessions, MFA enrollment, password reset, login history. Depends on: Service Layer (Identity-as-a-Service), Multi-Tenancy, Feature Flag / Global Control. Impact: The actual product surface — nothing is usable by a human without it. | Backlog
143 | Portals | Organization Admin Portal — user mgmt, allowed auth config, tenant audit/usage, branding | P2 | Service Layer (Identity-as-a-Service), Multi-Tenancy, Feature Flag / Global Control | The actual product surface — nothing is usable by a human without it | Implement: Organization Admin Portal — user mgmt, allowed auth config, tenant audit/usage, branding. Depends on: Service Layer (Identity-as-a-Service), Multi-Tenancy, Feature Flag / Global Control. Impact: The actual product surface — nothing is usable by a human without it. | Backlog
144 | Portals | Super Admin Portal — cross-tenant mgmt, feature flags, plan/tier mgmt, global audit | P2 | Service Layer (Identity-as-a-Service), Multi-Tenancy, Feature Flag / Global Control | The actual product surface — nothing is usable by a human without it | Implement: Super Admin Portal — cross-tenant mgmt, feature flags, plan/tier mgmt, global audit. Depends on: Service Layer (Identity-as-a-Service), Multi-Tenancy, Feature Flag / Global Control. Impact: The actual product surface — nothing is usable by a human without it. | Backlog
145 | Portals | Strict API-layer authorization boundaries between all three portals | P2 | Service Layer (Identity-as-a-Service), Multi-Tenancy, Feature Flag / Global Control | The actual product surface — nothing is usable by a human without it | Implement: Strict API-layer authorization boundaries between all three portals. Depends on: Service Layer (Identity-as-a-Service), Multi-Tenancy, Feature Flag / Global Control. Impact: The actual product surface — nothing is usable by a human without it. | Backlog
146 | Portals | Application Super Admin module — tenant list/management, global feature flags, global security parameters, plan/tier management, global audit, tenant lifecycle actions | P2 | Service Layer (Identity-as-a-Service), Multi-Tenancy, Feature Flag / Global Control | The actual product surface — nothing is usable by a human without it | Implement: Application Super Admin module — tenant list/management, global feature flags, global security parameters, plan/tier management, global audit, tenant lifecycle actions. Depends on: Service Layer (Identity-as-a-Service), Multi-Tenancy, Feature Flag / Global Control. Impact: The actual product surface — nothing is usable by a human without it. | Backlog
147 | Portals | Tenant/Organisation Admin module — tenant-scoped user management, tenant settings, tenant audit/usage view, feature config within Super-Admin-allowed set | P2 | Service Layer (Identity-as-a-Service), Multi-Tenancy, Feature Flag / Global Control | The actual product surface — nothing is usable by a human without it | Implement: Tenant/Organisation Admin module — tenant-scoped user management, tenant settings, tenant audit/usage view, feature config within Super-Admin-allowed set. Depends on: Service Layer (Identity-as-a-Service), Multi-Tenancy, Feature Flag / Global Control. Impact: The actual product surface — nothing is usable by a human without it. | Backlog
148 | Portals | User Profile Core Updates module — self-service profile edit (name/email/phone), password change, MFA device management, active session view/revoke | P2 | Service Layer (Identity-as-a-Service), Multi-Tenancy, Feature Flag / Global Control | The actual product surface — nothing is usable by a human without it | Implement: User Profile Core Updates module — self-service profile edit (name/email/phone), password change, MFA device management, active session view/revoke. Depends on: Service Layer (Identity-as-a-Service), Multi-Tenancy, Feature Flag / Global Control. Impact: The actual product surface — nothing is usable by a human without it. | Backlog
149 | Portals | Org Admin — Integrations Configuration module: enable/disable and configure integrations (social IDPs, WhatsApp, webhooks, etc.) per tenant | P2 | Service Layer (Identity-as-a-Service), Multi-Tenancy, Feature Flag / Global Control | The actual product surface — nothing is usable by a human without it | Implement: Org Admin — Integrations Configuration module: enable/disable and configure integrations (social IDPs, WhatsApp, webhooks, etc.) per tenant. Depends on: Service Layer (Identity-as-a-Service), Multi-Tenancy, Feature Flag / Global Control. Impact: The actual product surface — nothing is usable by a human without it. | Backlog
150 | Portals | Org Admin — API Key Management: create/rotate/revoke API keys/credentials for each enabled integration, scoped to that tenant | P2 | Service Layer (Identity-as-a-Service), Multi-Tenancy, Feature Flag / Global Control | The actual product surface — nothing is usable by a human without it | Implement: Org Admin — API Key Management: create/rotate/revoke API keys/credentials for each enabled integration, scoped to that tenant. Depends on: Service Layer (Identity-as-a-Service), Multi-Tenancy, Feature Flag / Global Control. Impact: The actual product surface — nothing is usable by a human without it. | Backlog
151 | Feature Flag / Global Control | Super Admin can enable/disable each feature globally or per tenant | P2 | Service Layer (Identity-as-a-Service) | Governs what every tenant/portal can see; needed before Portals can be feature-complete | Implement: Super Admin can enable/disable each feature globally or per tenant. Depends on: Service Layer (Identity-as-a-Service). Impact: Governs what every tenant/portal can see; needed before Portals can be feature-complete. | Backlog
152 | Feature Flag / Global Control | Each feature has a configurable default value/state | P2 | Service Layer (Identity-as-a-Service) | Governs what every tenant/portal can see; needed before Portals can be feature-complete | Implement: Each feature has a configurable default value/state. Depends on: Service Layer (Identity-as-a-Service). Impact: Governs what every tenant/portal can see; needed before Portals can be feature-complete. | Backlog
153 | Feature Flag / Global Control | Distinct from, but linked to, subscription entitlements | P2 | Service Layer (Identity-as-a-Service) | Governs what every tenant/portal can see; needed before Portals can be feature-complete | Implement: Distinct from, but linked to, subscription entitlements. Depends on: Service Layer (Identity-as-a-Service). Impact: Governs what every tenant/portal can see; needed before Portals can be feature-complete. | Backlog
154 | Feature Flag / Global Control | Per-tenant module enable/disable granularity — Super Admin controls which modules/features each individual tenant can access, not just global on/off | P2 | Service Layer (Identity-as-a-Service) | Governs what every tenant/portal can see; needed before Portals can be feature-complete | Implement: Per-tenant module enable/disable granularity — Super Admin controls which modules/features each individual tenant can access, not just global on/off. Depends on: Service Layer (Identity-as-a-Service). Impact: Governs what every tenant/portal can see; needed before Portals can be feature-complete. | Backlog
155 | Subscription & Billing | Tier/plan definition (SAML, MFA type, app count, MAU caps) | P2 | Multi-Tenancy, Portals, Feature Flag / Global Control | Unblocks monetization — nothing revenue-related works until this exists | Implement: Tier/plan definition (SAML, MFA type, app count, MAU caps). Depends on: Multi-Tenancy, Portals, Feature Flag / Global Control. Impact: Unblocks monetization — nothing revenue-related works until this exists. | Backlog
156 | Subscription & Billing | Tenant record: plan_id + status (active/past-due/suspended) | P2 | Multi-Tenancy, Portals, Feature Flag / Global Control | Unblocks monetization — nothing revenue-related works until this exists | Implement: Tenant record: plan_id + status (active/past-due/suspended). Depends on: Multi-Tenancy, Portals, Feature Flag / Global Control. Impact: Unblocks monetization — nothing revenue-related works until this exists. | Backlog
157 | Subscription & Billing | Entitlement enforcement middleware in Identity Service API | P2 | Multi-Tenancy, Portals, Feature Flag / Global Control | Unblocks monetization — nothing revenue-related works until this exists | Implement: Entitlement enforcement middleware in Identity Service API. Depends on: Multi-Tenancy, Portals, Feature Flag / Global Control. Impact: Unblocks monetization — nothing revenue-related works until this exists. | Backlog
158 | Subscription & Billing | Metering pipeline (event-driven off Keycloak events) | P2 | Multi-Tenancy, Portals, Feature Flag / Global Control | Unblocks monetization — nothing revenue-related works until this exists | Implement: Metering pipeline (event-driven off Keycloak events). Depends on: Multi-Tenancy, Portals, Feature Flag / Global Control. Impact: Unblocks monetization — nothing revenue-related works until this exists. | Backlog
159 | Subscription & Billing | Billing system integration (Stripe/similar) — external, hard boundary | P2 | Multi-Tenancy, Portals, Feature Flag / Global Control | Unblocks monetization — nothing revenue-related works until this exists | Implement: Billing system integration (Stripe/similar) — external, hard boundary. Depends on: Multi-Tenancy, Portals, Feature Flag / Global Control. Impact: Unblocks monetization — nothing revenue-related works until this exists. | Backlog
160 | Subscription & Billing | Dunning/suspension flow for past-due tenants | P2 | Multi-Tenancy, Portals, Feature Flag / Global Control | Unblocks monetization — nothing revenue-related works until this exists | Implement: Dunning/suspension flow for past-due tenants. Depends on: Multi-Tenancy, Portals, Feature Flag / Global Control. Impact: Unblocks monetization — nothing revenue-related works until this exists. | Backlog
161 | Subscription & Billing | Decision: v1 requirement vs bolted-on after internal rollout | P2 | Multi-Tenancy, Portals, Feature Flag / Global Control | Unblocks monetization — nothing revenue-related works until this exists | Implement: Decision: v1 requirement vs bolted-on after internal rollout. Depends on: Multi-Tenancy, Portals, Feature Flag / Global Control. Impact: Unblocks monetization — nothing revenue-related works until this exists. | Backlog
162 | Subscription & Billing | Plan-downgrade graceful handling (no silent breakage) | P2 | Multi-Tenancy, Portals, Feature Flag / Global Control | Unblocks monetization — nothing revenue-related works until this exists | Implement: Plan-downgrade graceful handling (no silent breakage). Depends on: Multi-Tenancy, Portals, Feature Flag / Global Control. Impact: Unblocks monetization — nothing revenue-related works until this exists. | Backlog
163 | Subscription & Billing | Overage behavior — hard cutoff vs soft billing vs grace period | P2 | Multi-Tenancy, Portals, Feature Flag / Global Control | Unblocks monetization — nothing revenue-related works until this exists | Implement: Overage behavior — hard cutoff vs soft billing vs grace period. Depends on: Multi-Tenancy, Portals, Feature Flag / Global Control. Impact: Unblocks monetization — nothing revenue-related works until this exists. | Backlog
164 | Subscription & Billing | Enterprise procurement support (MSA/DPA, security questionnaires) | P2 | Multi-Tenancy, Portals, Feature Flag / Global Control | Unblocks monetization — nothing revenue-related works until this exists | Implement: Enterprise procurement support (MSA/DPA, security questionnaires). Depends on: Multi-Tenancy, Portals, Feature Flag / Global Control. Impact: Unblocks monetization — nothing revenue-related works until this exists. | Backlog
165 | Subscription & Billing | Tenant Subscription module (portal) — plan view/upgrade/downgrade, billing/invoice history, usage/MAU dashboard for tenant admin | P2 | Multi-Tenancy, Portals, Feature Flag / Global Control | Unblocks monetization — nothing revenue-related works until this exists | Implement: Tenant Subscription module (portal) — plan view/upgrade/downgrade, billing/invoice history, usage/MAU dashboard for tenant admin. Depends on: Multi-Tenancy, Portals, Feature Flag / Global Control. Impact: Unblocks monetization — nothing revenue-related works until this exists. | Backlog
166 | Subscription & Billing | User Subscription module (portal) — per-user seat/license assignment within tenant plan, individual add-on entitlements if supported | P2 | Multi-Tenancy, Portals, Feature Flag / Global Control | Unblocks monetization — nothing revenue-related works until this exists | Implement: User Subscription module (portal) — per-user seat/license assignment within tenant plan, individual add-on entitlements if supported. Depends on: Multi-Tenancy, Portals, Feature Flag / Global Control. Impact: Unblocks monetization — nothing revenue-related works until this exists. | Backlog
167 | Subscription & Billing | On end-user signup, create User Subscription/seat record tied to tenant's plan automatically (not a manual admin step) | P2 | Multi-Tenancy, Portals, Feature Flag / Global Control | Unblocks monetization — nothing revenue-related works until this exists | Implement: On end-user signup, create User Subscription/seat record tied to tenant's plan automatically (not a manual admin step). Depends on: Multi-Tenancy, Portals, Feature Flag / Global Control. Impact: Unblocks monetization — nothing revenue-related works until this exists. | Backlog
168 | Security Concerns / Threat Model | Credential stuffing / brute force protection beyond Keycloak defaults | P3 | Every epic through Subscription & Billing (needs a real system to threat-model) | Validates the system built so far is actually safe to expose to real customers | Implement: Credential stuffing / brute force protection beyond Keycloak defaults. Depends on: Every epic through Subscription & Billing (needs a real system to threat-model). Impact: Validates the system built so far is actually safe to expose to real customers. | Backlog
169 | Security Concerns / Threat Model | Token theft/replay mitigation (storage practices in consuming apps) | P3 | Every epic through Subscription & Billing (needs a real system to threat-model) | Validates the system built so far is actually safe to expose to real customers | Implement: Token theft/replay mitigation (storage practices in consuming apps). Depends on: Every epic through Subscription & Billing (needs a real system to threat-model). Impact: Validates the system built so far is actually safe to expose to real customers. | Backlog
170 | Security Concerns / Threat Model | Open redirect prevention (strict redirect URI matching) | P3 | Every epic through Subscription & Billing (needs a real system to threat-model) | Validates the system built so far is actually safe to expose to real customers | Implement: Open redirect prevention (strict redirect URI matching). Depends on: Every epic through Subscription & Billing (needs a real system to threat-model). Impact: Validates the system built so far is actually safe to expose to real customers. | Backlog
171 | Security Concerns / Threat Model | Privilege escalation via client-supplied vs signed claims — audit | P3 | Every epic through Subscription & Billing (needs a real system to threat-model) | Validates the system built so far is actually safe to expose to real customers | Implement: Privilege escalation via client-supplied vs signed claims — audit. Depends on: Every epic through Subscription & Billing (needs a real system to threat-model). Impact: Validates the system built so far is actually safe to expose to real customers. | Backlog
172 | Security Concerns / Threat Model | Tenant isolation failure as a first-class test case | P3 | Every epic through Subscription & Billing (needs a real system to threat-model) | Validates the system built so far is actually safe to expose to real customers | Implement: Tenant isolation failure as a first-class test case. Depends on: Every epic through Subscription & Billing (needs a real system to threat-model). Impact: Validates the system built so far is actually safe to expose to real customers. | Backlog
173 | Security Concerns / Threat Model | Entitlement bypass prevention (enforce in API layer, not UI only) | P3 | Every epic through Subscription & Billing (needs a real system to threat-model) | Validates the system built so far is actually safe to expose to real customers | Implement: Entitlement bypass prevention (enforce in API layer, not UI only). Depends on: Every epic through Subscription & Billing (needs a real system to threat-model). Impact: Validates the system built so far is actually safe to expose to real customers. | Backlog
174 | Security Concerns / Threat Model | Billing/plan status desync check | P3 | Every epic through Subscription & Billing (needs a real system to threat-model) | Validates the system built so far is actually safe to expose to real customers | Implement: Billing/plan status desync check. Depends on: Every epic through Subscription & Billing (needs a real system to threat-model). Impact: Validates the system built so far is actually safe to expose to real customers. | Backlog
175 | Security Concerns / Threat Model | Social login account-takeover risk via auto-linking on email match | P3 | Every epic through Subscription & Billing (needs a real system to threat-model) | Validates the system built so far is actually safe to expose to real customers | Implement: Social login account-takeover risk via auto-linking on email match. Depends on: Every epic through Subscription & Billing (needs a real system to threat-model). Impact: Validates the system built so far is actually safe to expose to real customers. | Backlog
176 | Security Concerns / Threat Model | WhatsApp OTP weakness — not sole factor for privileged access | P3 | Every epic through Subscription & Billing (needs a real system to threat-model) | Validates the system built so far is actually safe to expose to real customers | Implement: WhatsApp OTP weakness — not sole factor for privileged access. Depends on: Every epic through Subscription & Billing (needs a real system to threat-model). Impact: Validates the system built so far is actually safe to expose to real customers. | Backlog
177 | Security Concerns / Threat Model | Secrets sprawl across consuming apps — least-privilege scoping | P3 | Every epic through Subscription & Billing (needs a real system to threat-model) | Validates the system built so far is actually safe to expose to real customers | Implement: Secrets sprawl across consuming apps — least-privilege scoping. Depends on: Every epic through Subscription & Billing (needs a real system to threat-model). Impact: Validates the system built so far is actually safe to expose to real customers. | Backlog
178 | Security Concerns / Threat Model | Admin console network isolation | P3 | Every epic through Subscription & Billing (needs a real system to threat-model) | Validates the system built so far is actually safe to expose to real customers | Implement: Admin console network isolation. Depends on: Every epic through Subscription & Billing (needs a real system to threat-model). Impact: Validates the system built so far is actually safe to expose to real customers. | Backlog
179 | Security Concerns / Threat Model | CVE/patch cadence for Keycloak + custom Authenticator SPIs | P3 | Every epic through Subscription & Billing (needs a real system to threat-model) | Validates the system built so far is actually safe to expose to real customers | Implement: CVE/patch cadence for Keycloak + custom Authenticator SPIs. Depends on: Every epic through Subscription & Billing (needs a real system to threat-model). Impact: Validates the system built so far is actually safe to expose to real customers. | Backlog
180 | Security Concerns / Threat Model | Audit log tamper-resistance (separate log store) | P3 | Every epic through Subscription & Billing (needs a real system to threat-model) | Validates the system built so far is actually safe to expose to real customers | Implement: Audit log tamper-resistance (separate log store). Depends on: Every epic through Subscription & Billing (needs a real system to threat-model). Impact: Validates the system built so far is actually safe to expose to real customers. | Backlog
181 | Security Concerns / Threat Model | PII minimization in federated claims | P3 | Every epic through Subscription & Billing (needs a real system to threat-model) | Validates the system built so far is actually safe to expose to real customers | Implement: PII minimization in federated claims. Depends on: Every epic through Subscription & Billing (needs a real system to threat-model). Impact: Validates the system built so far is actually safe to expose to real customers. | Backlog
182 | Security Concerns / Threat Model | Cross-border data residency for EU tenants | P3 | Every epic through Subscription & Billing (needs a real system to threat-model) | Validates the system built so far is actually safe to expose to real customers | Implement: Cross-border data residency for EU tenants. Depends on: Every epic through Subscription & Billing (needs a real system to threat-model). Impact: Validates the system built so far is actually safe to expose to real customers. | Backlog
183 | Security Concerns / Threat Model | SQL injection — parameterized queries/ORM in custom subsystems | P3 | Every epic through Subscription & Billing (needs a real system to threat-model) | Validates the system built so far is actually safe to expose to real customers | Implement: SQL injection — parameterized queries/ORM in custom subsystems. Depends on: Every epic through Subscription & Billing (needs a real system to threat-model). Impact: Validates the system built so far is actually safe to expose to real customers. | Backlog
184 | Security Concerns / Threat Model | Prompt injection — if any AI-assisted component has system access | P3 | Every epic through Subscription & Billing (needs a real system to threat-model) | Validates the system built so far is actually safe to expose to real customers | Implement: Prompt injection — if any AI-assisted component has system access. Depends on: Every epic through Subscription & Billing (needs a real system to threat-model). Impact: Validates the system built so far is actually safe to expose to real customers. | Backlog
185 | Security Concerns / Threat Model | LDAP injection — sanitize input into LDAP queries | P3 | Every epic through Subscription & Billing (needs a real system to threat-model) | Validates the system built so far is actually safe to expose to real customers | Implement: LDAP injection — sanitize input into LDAP queries. Depends on: Every epic through Subscription & Billing (needs a real system to threat-model). Impact: Validates the system built so far is actually safe to expose to real customers. | Backlog
186 | Security Concerns / Threat Model | XSS — custom admin portal, onboarding UI, Keycloak theme customizations | P3 | Every epic through Subscription & Billing (needs a real system to threat-model) | Validates the system built so far is actually safe to expose to real customers | Implement: XSS — custom admin portal, onboarding UI, Keycloak theme customizations. Depends on: Every epic through Subscription & Billing (needs a real system to threat-model). Impact: Validates the system built so far is actually safe to expose to real customers. | Backlog
187 | Security Concerns / Threat Model | CSRF — on custom Identity Service API state-changing endpoints | P3 | Every epic through Subscription & Billing (needs a real system to threat-model) | Validates the system built so far is actually safe to expose to real customers | Implement: CSRF — on custom Identity Service API state-changing endpoints. Depends on: Every epic through Subscription & Billing (needs a real system to threat-model). Impact: Validates the system built so far is actually safe to expose to real customers. | Backlog
188 | Security Concerns / Threat Model | XXE — SAML XML parsing | P3 | Every epic through Subscription & Billing (needs a real system to threat-model) | Validates the system built so far is actually safe to expose to real customers | Implement: XXE — SAML XML parsing. Depends on: Every epic through Subscription & Billing (needs a real system to threat-model). Impact: Validates the system built so far is actually safe to expose to real customers. | Backlog
189 | Security Concerns / Threat Model | Command injection — custom Authenticator SPIs / admin tooling | P3 | Every epic through Subscription & Billing (needs a real system to threat-model) | Validates the system built so far is actually safe to expose to real customers | Implement: Command injection — custom Authenticator SPIs / admin tooling. Depends on: Every epic through Subscription & Billing (needs a real system to threat-model). Impact: Validates the system built so far is actually safe to expose to real customers. | Backlog
190 | Security Concerns / Threat Model | Header injection / SSRF — URL-fetching subsystems (webhooks etc.) | P3 | Every epic through Subscription & Billing (needs a real system to threat-model) | Validates the system built so far is actually safe to expose to real customers | Implement: Header injection / SSRF — URL-fetching subsystems (webhooks etc.). Depends on: Every epic through Subscription & Billing (needs a real system to threat-model). Impact: Validates the system built so far is actually safe to expose to real customers. | Backlog
191 | Security Concerns / Threat Model | Input validation at every trust boundary | P3 | Every epic through Subscription & Billing (needs a real system to threat-model) | Validates the system built so far is actually safe to expose to real customers | Implement: Input validation at every trust boundary. Depends on: Every epic through Subscription & Billing (needs a real system to threat-model). Impact: Validates the system built so far is actually safe to expose to real customers. | Backlog
192 | Security Concerns / Threat Model | Audit custom subsystems for plaintext secret/PII exposure (logs, caches) | P3 | Every epic through Subscription & Billing (needs a real system to threat-model) | Validates the system built so far is actually safe to expose to real customers | Implement: Audit custom subsystems for plaintext secret/PII exposure (logs, caches). Depends on: Every epic through Subscription & Billing (needs a real system to threat-model). Impact: Validates the system built so far is actually safe to expose to real customers. | Backlog
193 | Security Concerns / Threat Model | Tenant-supplied API keys/credentials carry the same leakage/injection risk as platform secrets — must not be visible cross-tenant or logged in plaintext | P3 | Every epic through Subscription & Billing (needs a real system to threat-model) | Validates the system built so far is actually safe to expose to real customers | Implement: Tenant-supplied API keys/credentials carry the same leakage/injection risk as platform secrets — must not be visible cross-tenant or logged in plaintext. Depends on: Every epic through Subscription & Billing (needs a real system to threat-model). Impact: Validates the system built so far is actually safe to expose to real customers. | Backlog
194 | AWS IAM Federation | SAML/OIDC federation from Keycloak into AWS IAM roles | P3 | Cloud Infrastructure (AWS), Core Identity Provider | Niche — only needed if consuming services require AWS resource access via identity | Implement: SAML/OIDC federation from Keycloak into AWS IAM roles. Depends on: Cloud Infrastructure (AWS), Core Identity Provider. Impact: Niche — only needed if consuming services require AWS resource access via identity. | Backlog
195 | AWS IAM Federation | Role-mapping policy (identity claims → IAM roles) | P3 | Cloud Infrastructure (AWS), Core Identity Provider | Niche — only needed if consuming services require AWS resource access via identity | Implement: Role-mapping policy (identity claims → IAM roles). Depends on: Cloud Infrastructure (AWS), Core Identity Provider. Impact: Niche — only needed if consuming services require AWS resource access via identity. | Backlog
196 | AWS IAM Federation | Scope: which consuming services actually need AWS resource access | P3 | Cloud Infrastructure (AWS), Core Identity Provider | Niche — only needed if consuming services require AWS resource access via identity | Implement: Scope: which consuming services actually need AWS resource access. Depends on: Cloud Infrastructure (AWS), Core Identity Provider. Impact: Niche — only needed if consuming services require AWS resource access via identity. | Backlog
197 | Scalability | Peak target: ~1,000–5,000 req/s (revised down from 100k/s after sizing) | P3 | Core Identity Provider, Cloud Infrastructure (AWS) | Confirms the system holds up under real load before go-live | Implement: Peak target: ~1,000–5,000 req/s (revised down from 100k/s after sizing). Depends on: Core Identity Provider, Cloud Infrastructure (AWS). Impact: Confirms the system holds up under real load before go-live. | Backlog
198 | Scalability | Re-derive target if tenant/user assumptions grow materially | P3 | Core Identity Provider, Cloud Infrastructure (AWS) | Confirms the system holds up under real load before go-live | Implement: Re-derive target if tenant/user assumptions grow materially. Depends on: Core Identity Provider, Cloud Infrastructure (AWS). Impact: Confirms the system holds up under real load before go-live. | Backlog
199 | Scalability | Standard Keycloak HA cluster (2–3 nodes) — sufficient at current scale | P3 | Core Identity Provider, Cloud Infrastructure (AWS) | Confirms the system holds up under real load before go-live | Implement: Standard Keycloak HA cluster (2–3 nodes) — sufficient at current scale. Depends on: Core Identity Provider, Cloud Infrastructure (AWS). Impact: Confirms the system holds up under real load before go-live. | Backlog
200 | Scalability | Multi-region scoped to DR/availability, not throughput | P3 | Core Identity Provider, Cloud Infrastructure (AWS) | Confirms the system holds up under real load before go-live | Implement: Multi-region scoped to DR/availability, not throughput. Depends on: Core Identity Provider, Cloud Infrastructure (AWS). Impact: Confirms the system holds up under real load before go-live. | Backlog
201 | Scalability | Infinispan cache sizing/tuning under multi-tenant load | P3 | Core Identity Provider, Cloud Infrastructure (AWS) | Confirms the system holds up under real load before go-live | Implement: Infinispan cache sizing/tuning under multi-tenant load. Depends on: Core Identity Provider, Cloud Infrastructure (AWS). Impact: Confirms the system holds up under real load before go-live. | Backlog
202 | Scalability | DB connection pooling and read-replica strategy under growth | P3 | Core Identity Provider, Cloud Infrastructure (AWS) | Confirms the system holds up under real load before go-live | Implement: DB connection pooling and read-replica strategy under growth. Depends on: Core Identity Provider, Cloud Infrastructure (AWS). Impact: Confirms the system holds up under real load before go-live. | Backlog
203 | Scalability | Token validation path scaling (JWKS caching — verify holds under load) | P3 | Core Identity Provider, Cloud Infrastructure (AWS) | Confirms the system holds up under real load before go-live | Implement: Token validation path scaling (JWKS caching — verify holds under load). Depends on: Core Identity Provider, Cloud Infrastructure (AWS). Impact: Confirms the system holds up under real load before go-live. | Backlog
204 | Scalability | Load testing plan (login throughput, token issuance, concurrent sessions) | P3 | Core Identity Provider, Cloud Infrastructure (AWS) | Confirms the system holds up under real load before go-live | Implement: Load testing plan (login throughput, token issuance, concurrent sessions). Depends on: Core Identity Provider, Cloud Infrastructure (AWS). Impact: Confirms the system holds up under real load before go-live. | Backlog
205 | Observability & Ops | Auth metrics dashboard (login success/failure, latency, MFA rate) | P3 | Core Identity Provider, Cloud Infrastructure (AWS) | Required before trusting the system in production — can't operate what you can't see | Implement: Auth metrics dashboard (login success/failure, latency, MFA rate). Depends on: Core Identity Provider, Cloud Infrastructure (AWS). Impact: Required before trusting the system in production — can't operate what you can't see. | Backlog
206 | Observability & Ops | Audit logging — queryable, every auth event and admin change | P3 | Core Identity Provider, Cloud Infrastructure (AWS) | Required before trusting the system in production — can't operate what you can't see | Implement: Audit logging — queryable, every auth event and admin change. Depends on: Core Identity Provider, Cloud Infrastructure (AWS). Impact: Required before trusting the system in production — can't operate what you can't see. | Backlog
207 | Observability & Ops | Incident runbook for system-wide auth outage | P3 | Core Identity Provider, Cloud Infrastructure (AWS) | Required before trusting the system in production — can't operate what you can't see | Implement: Incident runbook for system-wide auth outage. Depends on: Core Identity Provider, Cloud Infrastructure (AWS). Impact: Required before trusting the system in production — can't operate what you can't see. | Backlog
208 | Observability & Ops | Ops/Audit Console | P3 | Core Identity Provider, Cloud Infrastructure (AWS) | Required before trusting the system in production — can't operate what you can't see | Implement: Ops/Audit Console. Depends on: Core Identity Provider, Cloud Infrastructure (AWS). Impact: Required before trusting the system in production — can't operate what you can't see. | Backlog
209 | Observability & Ops | Login-failure debugging tooling for support (cross-tenant safe) | P3 | Core Identity Provider, Cloud Infrastructure (AWS) | Required before trusting the system in production — can't operate what you can't see | Implement: Login-failure debugging tooling for support (cross-tenant safe). Depends on: Core Identity Provider, Cloud Infrastructure (AWS). Impact: Required before trusting the system in production — can't operate what you can't see. | Backlog
210 | Resilience | Failure mode: LDAP unreachable — fail closed vs cached sessions | P3 | Cloud Infrastructure (AWS), Scalability | Defines what happens when something breaks; needed before any uptime commitment | Implement: Failure mode: LDAP unreachable — fail closed vs cached sessions. Depends on: Cloud Infrastructure (AWS), Scalability. Impact: Defines what happens when something breaks; needed before any uptime commitment. | Backlog
211 | Resilience | Failure mode: Keycloak node down — cluster failover behavior | P3 | Cloud Infrastructure (AWS), Scalability | Defines what happens when something breaks; needed before any uptime commitment | Implement: Failure mode: Keycloak node down — cluster failover behavior. Depends on: Cloud Infrastructure (AWS), Scalability. Impact: Defines what happens when something breaks; needed before any uptime commitment. | Backlog
212 | Resilience | Failure mode: SAML mapping breaks post-upgrade — smoke test in deploy pipeline | P3 | Cloud Infrastructure (AWS), Scalability | Defines what happens when something breaks; needed before any uptime commitment | Implement: Failure mode: SAML mapping breaks post-upgrade — smoke test in deploy pipeline. Depends on: Cloud Infrastructure (AWS), Scalability. Impact: Defines what happens when something breaks; needed before any uptime commitment. | Backlog
213 | Resilience | Disaster recovery — cross-region backup/restore of Keycloak DB + realm config | P3 | Cloud Infrastructure (AWS), Scalability | Defines what happens when something breaks; needed before any uptime commitment | Implement: Disaster recovery — cross-region backup/restore of Keycloak DB + realm config. Depends on: Cloud Infrastructure (AWS), Scalability. Impact: Defines what happens when something breaks; needed before any uptime commitment. | Backlog
214 | Compliance & Certification | Audit log retention policy | P3 | Security Concerns / Threat Model, Security Parameters | Unblocks enterprise sales; long lead time — should start once the core system stabilizes, not after | Implement: Audit log retention policy. Depends on: Security Concerns / Threat Model, Security Parameters. Impact: Unblocks enterprise sales; long lead time — should start once the core system stabilizes, not after. | Backlog
215 | Compliance & Certification | Data residency for EU tenants | P3 | Security Concerns / Threat Model, Security Parameters | Unblocks enterprise sales; long lead time — should start once the core system stabilizes, not after | Implement: Data residency for EU tenants. Depends on: Security Concerns / Threat Model, Security Parameters. Impact: Unblocks enterprise sales; long lead time — should start once the core system stabilizes, not after. | Backlog
216 | Compliance & Certification | Right-to-erasure / user data deletion process | P3 | Security Concerns / Threat Model, Security Parameters | Unblocks enterprise sales; long lead time — should start once the core system stabilizes, not after | Implement: Right-to-erasure / user data deletion process. Depends on: Security Concerns / Threat Model, Security Parameters. Impact: Unblocks enterprise sales; long lead time — should start once the core system stabilizes, not after. | Backlog
217 | Compliance & Certification | SOC 2 / GDPR readiness assessment | P3 | Security Concerns / Threat Model, Security Parameters | Unblocks enterprise sales; long lead time — should start once the core system stabilizes, not after | Implement: SOC 2 / GDPR readiness assessment. Depends on: Security Concerns / Threat Model, Security Parameters. Impact: Unblocks enterprise sales; long lead time — should start once the core system stabilizes, not after. | Backlog
218 | Compliance & Certification | SOC 2 certification roadmap — flagged as sales blocker, long lead time | P3 | Security Concerns / Threat Model, Security Parameters | Unblocks enterprise sales; long lead time — should start once the core system stabilizes, not after | Implement: SOC 2 certification roadmap — flagged as sales blocker, long lead time. Depends on: Security Concerns / Threat Model, Security Parameters. Impact: Unblocks enterprise sales; long lead time — should start once the core system stabilizes, not after. | Backlog
219 | Migration & Cutover | Discovery — inventory of every app/API, current vs target auth method | P3 | SAML Integration, OIDC / App Authentication, Directory Federation (LDAP/AD) | Actually moves existing apps (BOE, etc.) onto the new system — the real go-live step | Implement: Discovery — inventory of every app/API, current vs target auth method. Depends on: SAML Integration, OIDC / App Authentication, Directory Federation (LDAP/AD). Impact: Actually moves existing apps (BOE, etc.) onto the new system — the real go-live step. | Backlog
220 | Migration & Cutover | App-by-app cutover plan per phase | P3 | SAML Integration, OIDC / App Authentication, Directory Federation (LDAP/AD) | Actually moves existing apps (BOE, etc.) onto the new system — the real go-live step | Implement: App-by-app cutover plan per phase. Depends on: SAML Integration, OIDC / App Authentication, Directory Federation (LDAP/AD). Impact: Actually moves existing apps (BOE, etc.) onto the new system — the real go-live step. | Backlog
221 | Migration & Cutover | Explicit decommission of legacy auth paths (no dormant bypasses) | P3 | SAML Integration, OIDC / App Authentication, Directory Federation (LDAP/AD) | Actually moves existing apps (BOE, etc.) onto the new system — the real go-live step | Implement: Explicit decommission of legacy auth paths (no dormant bypasses). Depends on: SAML Integration, OIDC / App Authentication, Directory Federation (LDAP/AD). Impact: Actually moves existing apps (BOE, etc.) onto the new system — the real go-live step. | Backlog
222 | Onboarding & Migration Experience | Developer documentation/SDK quality for integration | P4 | Service Layer (Identity-as-a-Service), Migration & Cutover | Determines how painful it is for a new customer to actually adopt the product | Implement: Developer documentation/SDK quality for integration. Depends on: Service Layer (Identity-as-a-Service), Migration & Cutover. Impact: Determines how painful it is for a new customer to actually adopt the product. | Backlog
223 | Onboarding & Migration Experience | Sandbox/staging environment for pre-production testing | P4 | Service Layer (Identity-as-a-Service), Migration & Cutover | Determines how painful it is for a new customer to actually adopt the product | Implement: Sandbox/staging environment for pre-production testing. Depends on: Service Layer (Identity-as-a-Service), Migration & Cutover. Impact: Determines how painful it is for a new customer to actually adopt the product. | Backlog
224 | Onboarding & Migration Experience | Migration cutover plan with rollback path | P4 | Service Layer (Identity-as-a-Service), Migration & Cutover | Determines how painful it is for a new customer to actually adopt the product | Implement: Migration cutover plan with rollback path. Depends on: Service Layer (Identity-as-a-Service), Migration & Cutover. Impact: Determines how painful it is for a new customer to actually adopt the product. | Backlog
225 | Onboarding & Migration Experience | Migration downtime/risk communication to customers | P4 | Service Layer (Identity-as-a-Service), Migration & Cutover | Determines how painful it is for a new customer to actually adopt the product | Implement: Migration downtime/risk communication to customers. Depends on: Service Layer (Identity-as-a-Service), Migration & Cutover. Impact: Determines how painful it is for a new customer to actually adopt the product. | Backlog
226 | Account Recovery | Self-service password reset flow | P4 | MFA, OIDC / App Authentication | Directly determines post-launch support ticket volume | Implement: Self-service password reset flow. Depends on: MFA, OIDC / App Authentication. Impact: Directly determines post-launch support ticket volume. | Backlog
227 | Account Recovery | Lost-MFA-device recovery flow | P4 | MFA, OIDC / App Authentication | Directly determines post-launch support ticket volume | Implement: Lost-MFA-device recovery flow. Depends on: MFA, OIDC / App Authentication. Impact: Directly determines post-launch support ticket volume. | Backlog
228 | Account Recovery | Clear in-UI session/logout messaging (idle vs absolute timeout) | P4 | MFA, OIDC / App Authentication | Directly determines post-launch support ticket volume | Implement: Clear in-UI session/logout messaging (idle vs absolute timeout). Depends on: MFA, OIDC / App Authentication. Impact: Directly determines post-launch support ticket volume. | Backlog
229 | Account Recovery | Tenant-configurable password/MFA strictness within platform limits | P4 | MFA, OIDC / App Authentication | Directly determines post-launch support ticket volume | Implement: Tenant-configurable password/MFA strictness within platform limits. Depends on: MFA, OIDC / App Authentication. Impact: Directly determines post-launch support ticket volume. | Backlog
230 | Reliability & Incident Communication | Public status page | P4 | Observability & Ops, Resilience | Determines customer trust during incidents | Implement: Public status page. Depends on: Observability & Ops, Resilience. Impact: Determines customer trust during incidents. | Backlog
231 | Reliability & Incident Communication | Proactive incident communication process | P4 | Observability & Ops, Resilience | Determines customer trust during incidents | Implement: Proactive incident communication process. Depends on: Observability & Ops, Resilience. Impact: Determines customer trust during incidents. | Backlog
232 | Reliability & Incident Communication | Third-party IDP outage dependency handling/communication | P4 | Observability & Ops, Resilience | Determines customer trust during incidents | Implement: Third-party IDP outage dependency handling/communication. Depends on: Observability & Ops, Resilience. Impact: Determines customer trust during incidents. | Backlog
233 | Reliability & Incident Communication | SLA definition and monitoring | P4 | Observability & Ops, Resilience | Determines customer trust during incidents | Implement: SLA definition and monitoring. Depends on: Observability & Ops, Resilience. Impact: Determines customer trust during incidents. | Backlog
234 | Reliability & Incident Communication | Super Admin global policy changes reviewed for tenant impact before rollout | P4 | Observability & Ops, Resilience | Determines customer trust during incidents | Implement: Super Admin global policy changes reviewed for tenant impact before rollout. Depends on: Observability & Ops, Resilience. Impact: Determines customer trust during incidents. | Backlog
235 | Trust & Transparency | Real-time usage/MAU visibility for tenant admins | P4 | Subscription & Billing, Portals | Determines enterprise buyer confidence and reduces billing disputes | Implement: Real-time usage/MAU visibility for tenant admins. Depends on: Subscription & Billing, Portals. Impact: Determines enterprise buyer confidence and reduces billing disputes. | Backlog
236 | Trust & Transparency | Tenant isolation documentation/evidence for security reviews | P4 | Subscription & Billing, Portals | Determines enterprise buyer confidence and reduces billing disputes | Implement: Tenant isolation documentation/evidence for security reviews. Depends on: Subscription & Billing, Portals. Impact: Determines enterprise buyer confidence and reduces billing disputes. | Backlog
237 | Trust & Transparency | Stated data-portability/export commitment | P4 | Subscription & Billing, Portals | Determines enterprise buyer confidence and reduces billing disputes | Implement: Stated data-portability/export commitment. Depends on: Subscription & Billing, Portals. Impact: Determines enterprise buyer confidence and reduces billing disputes. | Backlog
238 | Trust & Transparency | Tenant-level audit trail (admin's own change history) | P4 | Subscription & Billing, Portals | Determines enterprise buyer confidence and reduces billing disputes | Implement: Tenant-level audit trail (admin's own change history). Depends on: Subscription & Billing, Portals. Impact: Determines enterprise buyer confidence and reduces billing disputes. | Backlog
239 | Trust & Transparency | Stated data-deletion policy/timeline after offboarding | P4 | Subscription & Billing, Portals | Determines enterprise buyer confidence and reduces billing disputes | Implement: Stated data-deletion policy/timeline after offboarding. Depends on: Subscription & Billing, Portals. Impact: Determines enterprise buyer confidence and reduces billing disputes. | Backlog
240 | Trust & Transparency | Tenant-specific incident impact visibility (not just global status) | P4 | Subscription & Billing, Portals | Determines enterprise buyer confidence and reduces billing disputes | Implement: Tenant-specific incident impact visibility (not just global status). Depends on: Subscription & Billing, Portals. Impact: Determines enterprise buyer confidence and reduces billing disputes. | Backlog
241 | Performance & Latency | Geographic latency evaluation for globally distributed tenant users | P4 | Scalability, Cloud Infrastructure (AWS) | Affects user experience for globally distributed tenant users | Implement: Geographic latency evaluation for globally distributed tenant users. Depends on: Scalability, Cloud Infrastructure (AWS). Impact: Affects user experience for globally distributed tenant users. | Backlog
242 | Performance & Latency | Rate-limiting tuning to avoid false-positive throttling | P4 | Scalability, Cloud Infrastructure (AWS) | Affects user experience for globally distributed tenant users | Implement: Rate-limiting tuning to avoid false-positive throttling. Depends on: Scalability, Cloud Infrastructure (AWS). Impact: Affects user experience for globally distributed tenant users. | Backlog
243 | Support & Change Management | Support tier differentiation by plan | P4 | Portals, Service Layer (Identity-as-a-Service) API versioning | Determines ongoing operational/support cost post-launch | Implement: Support tier differentiation by plan. Depends on: Portals, Service Layer (Identity-as-a-Service) API versioning. Impact: Determines ongoing operational/support cost post-launch. | Backlog
244 | Support & Change Management | Clear escalation boundary — tenant's users → tenant vs platform support | P4 | Portals, Service Layer (Identity-as-a-Service) API versioning | Determines ongoing operational/support cost post-launch | Implement: Clear escalation boundary — tenant's users → tenant vs platform support. Depends on: Portals, Service Layer (Identity-as-a-Service) API versioning. Impact: Determines ongoing operational/support cost post-launch. | Backlog
245 | Support & Change Management | API/SDK breaking-change notification process | P4 | Portals, Service Layer (Identity-as-a-Service) API versioning | Determines ongoing operational/support cost post-launch | Implement: API/SDK breaking-change notification process. Depends on: Portals, Service Layer (Identity-as-a-Service) API versioning. Impact: Determines ongoing operational/support cost post-launch. | Backlog

## Summary
Epic | Item Count | Priority Tier | Depends On
Core Identity Provider | 5 | P0 | Technology Stack (backend runtime)
Security Parameters | 18 | P0 | None — can be decided in parallel with infra setup
Cloud Infrastructure (AWS) | 12 | P0 | Core Identity Provider (hosting target)
Containerization / Docker | 18 | P0 | Core Identity Provider, Technology Stack
Technology Stack | 5 | P0 | None — foundational decision
Directory Federation (LDAP/AD) | 10 | P0 | Core Identity Provider
Governance & Control Plane | 3 | P0 | Core Identity Provider
SAML Integration | 4 | P1 | Core Identity Provider, Directory Federation (LDAP/AD)
OIDC / App Authentication | 3 | P1 | Core Identity Provider, Directory Federation (LDAP/AD)
API Authentication | 3 | P1 | Core Identity Provider
MFA | 5 | P1 | OIDC / App Authentication, SAML Integration
Authorization | 3 | P1 | OIDC / App Authentication, API Authentication
Social Login | 7 | P1 | OIDC / App Authentication
WhatsApp Integration | 5 | P1 | MFA (as an OTP channel)
Multiple IDPs (Identity Brokering) | 4 | P1 | Social Login, SAML Integration, Directory Federation (LDAP/AD)
Authenticator Integrator | 3 | P1 | MFA, WhatsApp Integration
Service Layer (Identity-as-a-Service) | 8 | P2 | Core Identity Provider, OIDC / App Authentication, API Authentication
Multi-Tenancy | 7 | P2 | Service Layer (Identity-as-a-Service)
User Import/Export | 18 | P2 | Multi-Tenancy, Directory Federation (LDAP/AD)
Portals | 9 | P2 | Service Layer (Identity-as-a-Service), Multi-Tenancy, Feature Flag / Global Control
Feature Flag / Global Control | 4 | P2 | Service Layer (Identity-as-a-Service)
Subscription & Billing | 13 | P2 | Multi-Tenancy, Portals, Feature Flag / Global Control
Security Concerns / Threat Model | 26 | P3 | Every epic through Subscription & Billing (needs a real system to threat-model)
AWS IAM Federation | 3 | P3 | Cloud Infrastructure (AWS), Core Identity Provider
Scalability | 8 | P3 | Core Identity Provider, Cloud Infrastructure (AWS)
Observability & Ops | 5 | P3 | Core Identity Provider, Cloud Infrastructure (AWS)
Resilience | 4 | P3 | Cloud Infrastructure (AWS), Scalability
Compliance & Certification | 5 | P3 | Security Concerns / Threat Model, Security Parameters
Migration & Cutover | 3 | P3 | SAML Integration, OIDC / App Authentication, Directory Federation (LDAP/AD)
Onboarding & Migration Experience | 4 | P4 | Service Layer (Identity-as-a-Service), Migration & Cutover
Account Recovery | 4 | P4 | MFA, OIDC / App Authentication
Reliability & Incident Communication | 5 | P4 | Observability & Ops, Resilience
Trust & Transparency | 6 | P4 | Subscription & Billing, Portals
Performance & Latency | 2 | P4 | Scalability, Cloud Infrastructure (AWS)
Support & Change Management | 3 | P4 | Portals, Service Layer (Identity-as-a-Service) API versioning
TOTAL | 245